## Sheet1
Stories | Tasks | Resposible | Status | 2014-08-22 | 2014-08-23 | 2014-08-24 | 2014-08-25 | 2014-08-26 | 2014-08-27 | 2014-08-28 | 2014-08-29 | 2014-08-30 | 2014-08-31 | 2014-09-01 | 2014-09-02 | 2014-09-03 | 2014-09-04 | 2014-09-05 | 2014-09-06 | 2014-09-07 | 2014-09-08 | 2014-09-09 | 2014-09-10 | 2014-09-11 | 2014-09-12 | 2014-09-13 | 2014-09-14 | 2014-09-15 | 2014-09-16 | 2014-09-17 | 2014-09-18 | 2014-09-19
M1 | Wiki page |  |  | 2014-08-22: 1; 2014-08-23: 1; 2014-08-24: 1; 2014-08-25: 1; 2014-08-26: 0
| Team Contract |  |  | 2014-08-22: 1; 2014-08-23: 1; 2014-08-24: 1; 2014-08-25: 1; 2014-08-26: 0
| Sprint BackLog |  |  | 2014-08-22: 1; 2014-08-23: 1; 2014-08-24: 1; 2014-08-25: 1; 2014-08-26: 1; 2014-08-27: 0.5
| Product BackLog |  |  | 2014-08-22: 1; 2014-08-23: 1; 2014-08-24: 1; 2014-08-25: 1; 2014-08-26: 1; 2014-08-27: 0.5
M2 | Git Set-up | bar: 2014-08-22
Edit and commit files with Git | bar: 2014-08-22
Add and remove files with Git | bar: 2014-08-22
Gradle Set-up | bar: 2014-08-22
| Build with Gradle |  |  | 2014-08-22: 2
M3 | Create a Context Diagram |  |  | 2014-08-22: 2
Brainstorm 10 use cases | bar: 2014-08-22
| Opening and welcome screen |  |  | 2014-08-22: 3
| Configuration Dialog |  |  | 2014-08-22: 3
| Create an object in model |  |  | 2014-08-22: 3
M4 | Create the Domain Model for the application |  |  | 2014-08-22: 5
| List primary attributes |  |  | 2014-08-22: 2
| Design classes hierarchy |  |  | 2014-08-22: 2